Community Health Needs Assessment

2021 Implementation Plan

- Mental Health

- Chronic Conditions

- Healthy Aging

- Health Equity

- Cancer Treatment and Prevention

| Mental Health Interventions | December 2022 | December 2023 | December 2024 |
| --- | --- | --- | --- |
| Increase depression screenings in Primary Care/OBGYN/ED through SBINS (screening, brief intervention, navigation to services) screenings | - Continued with Four Seasons on SBINS Screening. - Exploring the health record to streamline process |  |  |
| Explore LICSW's in Primary Care and Inpatient Care Management to support team-based care to meet psychosocial needs of patients identified through Social Determinant of Health screenings | Meetings set up with Primary Care Department to start work on expanding team-based care including social workers |  |  |
| Increase employee literacy in Trauma Responsive Care and integrating trauma responsive practice into BMH culture. | Working with JEDI Committee |  |  |
| Increase number of care plans for people who have high utilization in the ER through the use of embedded Psychiatric NP in the ER | Continued support of Psychiatric Nurse Practitioner in the ED |  |  |
| Continue to provide an embedded Psychologist within Brattleboro Family Medicine to serve the Medical Group | Continued support |  |  |
| Continue to Support the Community Health Team and the Women’s Health Initiative | Continued support |  |  |
| Continue facilitation and participation in the Regional Psychiatric Strategy Committee | Continued support |  |  |
| Continue to explore Healthworks ACT | Funding raised for Healthworks ACT. Plan to start program in early 2023 |  |  |

| Chronic Conditions Interventions | 2022 | 2023 | 2024 |
| --- | --- | --- | --- |
| Create an Outpatient Quality Improvement Manger position to focus on Chronic Condition Quality Improvement | Completed. |  |  |
| Explore Quality Improvement and Population Health structure to align organizational priorities for a larger impact in chronic conditions | Completed. |  |  |
| Diabetes Continue to support the following: - Diabetes Prevention Self-Management Program - Diabetes Management Self-Management Program - Community Health Team - Jim Harris, APRN Collaboration - PCMH New Interventions to explore: - Onboard Podiatrist - Onboard Ophthalmologist | Continued support for all areas below Completed Onboarding |  |  |
| Substance Use Disorder Continue to support: - Consortium on Substance Use - Opioid Task Force - Administrative responsibility for the Hub and spoke program - Narcan Distribution - Medication Take Back program New Interventions to explore: - Healthworks ACT - Alcohol Use Disorder ambulatory medication management program | Grant ended. Discontinued Continued Support Continued Support Continued Support Continued Support Starting in 2023 Continued Exploration with community partners |  |  |
| Hypertension Continue to support the following: - PCMH - One Care Vermont - CHT New Interventions to explore: - HTN Self-Management Program - Cardiac Prehab Program - Cardiac Clinical Community- Readmissions | Continued Support for the programs below Continued Support Possible restart in 2023 Not yet started |  |  |
| COPD Continue to support the following: - Clinical Community Task force including readmission rates, coordinated education and pharmacological formularies - CHT - One Care Vermont New Interventions to explore: - Pulmonologist collaboration with Cheshire | Continued Support and development Continued Support Continued Support On-site support developed |  |  |
| CHF Continue to support the following: - Cardiology department New Interventions to explore: - Clinical Community Task force including readmission rates, coordinated education and pharmacological formularies | Continued Support Continued Support and development |  |  |

| Healthy Aging Interventions | 2022 | 2023 | 2024 |
| --- | --- | --- | --- |
| Develop a Worksite wellness program at BMH | Not yet developed |  |  |
| Rehab space for better access and prevention programs | Completed- Rehab services moved to a new space |  |  |
| Primary Care RN Wellness Visits | In development |  |  |
| Continue to support community wellness programs - Tai Chi - Chair Yoga - Pool Program | - Continue to support community wellness programs. - Pool program on pause due to access to a pool |  |  |
| Continue to support readmission projects for high utilization diseases | Continued Support and development |  |  |

| Health Equity Interventions | 2022 | 2023 | 2024 |
| --- | --- | --- | --- |
| Onboard a Director of Diversity (DEI), Equity and Inclusion | On hold |  |  |
| Create a Diversity, Equity and Inclusion Council | Completed- Added Justice to be a JEDI committee |  |  |
| Continue to support the Council on Racial Equity (CORE) | Integrated with a Justice, Equity, Diversity and Inclusion (JEDI)committee |  |  |
| Continue to support the LGBTQ+ Committee | Integrated with a Justice, Equity, Diversity and Inclusion (JEDI)committee |  |  |
| Mandatory Education /Elsevier on DEI culture at BMH | In development with consultants |  |  |
| Increase accurate race & ethnicity data collection | In development with consultants |  |  |
| Develop focused interventions based on health inequities within BMH Health Service Area BIPOC community | In development with consultants |  |  |
| Expand Healthworks to an Assertive Community Treatment (ACT) model with collaboration with Groundworks, HCRS, and the Brattleboro Retreat | Completed- Program expected to go live in early 2023 |  |  |
| Provide targeted outreach for services | In development |  |  |

| Cancer Treatment & Prevention Interventions | 2022 | 2023 | 2024 |
| --- | --- | --- | --- |
| Explore BMH Oncology/Infusion expansion | Discussion has started and entering in proposal phase |  |  |
| Explore Colorectal VDH Grants | In progress with the Quality Team |  |  |
| Explore Breast and Cervical Cancer VDH Grants | In progress with the Quality Team |  |  |
| Increase colorectal screening rates | In progress with the Quality Team |  |  |
| Increase mammogram and cervical cancer screening rates | In progress with the Quality Team |  |  |
| Explore risk ranking practices for breast cancer | Not yet started |  |  |
| Explore collaboration with Cheshire Medical Center’s Norton Cancer program | Not yet started |  |  |
| Continue to support Breast Navigator | Continue to Support |  |  |